## Borehole Datasets
Dataset | Dataset name | Dataset description and requirements | Format | Data type | Publication | Planned acquisition (Yes/No) | Acquired (Yes/No) | Status (Missing / Not acquired / Available) | Due date | Date delivered | # Items | Comment
01 | Planning | All documents related to the planning of drilling, logging and testing activities
01.01 | Drilling programme (or Well Programme) | The formal document that details the overall plan for drilling the wellbore proposed to the authorities. It includes the well objectives, design, trajectory, casing and cementing program, mud program, expected formations, hazards, logging plan, testing program, contingency plans, and HSE considerations. | .pdf | Report | yes
01.02 | Completion / Workover / Plug and Abandonment Programme | Well completion / B workover / plug and abandonment programme | .pdf | Report | yes
01.03 | Permits for well planning | Copy of any relevant and available permit that helps to revisit and understand the activities at the wellsite. These documents are not mandatory for submission; the list below is non-exhaustive and only provided as examples. A. Well construction and drilling: site preparation / civil works, water use or discharge, waste management. B. HSE-related permits: environmental impact assessment, air emission, noise/vibration, use of radioactive sources (import and use), explosives, chemical use/transport (hazardous substances), radiation protection plan (if issued separately), occupational HSE permits (e.g. confined space, lifting). C. Import/export & customs: rigs, logging equipment, radioactive sources, heavy equipment. D. Third-party & local authority approvals: local authority permits (e.g. fire department), security permits, emergency response plan approval (e.g. blowout contingency). | .pdf | Report | no
01.04 | Drilling Schedule | Drilling schedule: a timeline of the planned operations from spud to TD, including a graphical representation of expected progress in depth vs. Time. May be part of the drilling programme Drilling lookaheads: short documents (typically weekly) showing the upcoming operations, expected progress vs. time, and key requirements (personnel, equipment, logistics) | .pdf | Report | no
02 | Daily Drilling Reports (DDR)
02.01 | Daily drilling reports (DDR) | All daily drilling reports (DDR), covering every calendar day for the entire drilling period, from spud until rig release. These are standardised industry documents that record daily drilling activities, performance, and progress. Typical contents include: - Well and time information: date, well name, report number, 24-hr period covered. - Depths: start/end depth, hole size, bit size, bit depth. - Operations summary: activities performed in the last 24 hours, current operation, planned next steps. - Drilling parameters: ROP, WOB, RPM, torque, pump rates, pressures. - Mud information: type, properties, volumes. - Casing and cementing (if applicable): strings run, cement volumes, results. - Bit/BHA details: bit type, BHA configuration, performance. - Non-productive time (NPT) / downtime: description and duration. - Logistics & personnel: personnel on board (POB), equipment arrivals/departures. - HSE events: incidents, near misses, safety observations. | .pdf | Report | yes
02.02 | Weekly drilling reports | If issued, weekly drilling summaries may also be provided. Higher-level summary over a 7-day period, typically including: - Summary of operations and progress vs. plan. - Cumulative depth, time breakdown, NPT analysis. - Key events and decisions. - Lessons learned / operational risks. - Forecast of next week’s activities. | .pdf | Report | yes
03 | Daily Mud Reports (DMR)
03.01 | Daily mud reports (DMR) | All daily mud reports (DMR), covering every calendar day for the entire drilling period, from spud until rig release. Typically includes information such as mud properties, solid analysis, mud rheology and hydraulics, material, volumes, circulation data. | .pdf | Report | yes
04 | Daily Geological Reports (DGR)
04.01 | Daily geological reports (DGR) | All daily mud reports (DGR), covering every calendar day for the entire drilling period, from spud until rig release. Typically includes information such as drilling progress, lithological descriptions, hydrocarbon gas shows, stratigraphy, operations summary, remarks, core description (if any) | .pdf | Report | yes
05 | Measurements While Drilling (MWD) | MWD are downhole drilling measurements recorded in real time
05.01 | Measurements While Drilling (MWD) | These data are delivered for the intervals where MWD tools were run in the BHA. They consist of downhole drilling measurements recorded in real time, typically provided depth-indexed (sometimes time-indexed) in tabular or digital formats (e.g. ASCII, WITSML, LAS), sometimes in graphical format too (e.g. logplot in .pdf) Typical measurements include, for example: - Directional data: inclination, azimuth. - Downhole drilling parameters: weight on bit, torque, RPM, annular pressure, downhole temperature. Note: MWD/LWD data are downhole measurements. Surface drilling parameters measured by rig sensors (hookload, pump strokes, standpipe pressure, etc.) are reported separately under category 06 Mud Logging. | .las .ascii .pdf | Data | yes
06 | Mud Logging | Mud logs provide a graphical representation of data measured at the surface, often referred to as master logs. The same data in digital format shall also be provided depth-indexed and time-indexed when applicable.
06.01 | Mud logging data | Typical contents include: - Lithological descriptions of cuttings and hydrocarbon shows. - Surface drilling parameters measured by rig sensors (ROP, hookload, rotary RPM, pump strokes, standpipe pressure, torque at surface). - Mud data (density, viscosity, flow rates, pit volumes). - Gas monitoring (total gas, chromatographic breakdown C1–C5+, connection/trip gases, and any abnormal peaks or anomalies). - Sampling records (cuttings, fluids, gas samples, core catch points). - Notable events (pressure anomalies, well control events). Formats: - Final comprehensive mud log (master log) covering the entire well: PDF, TIFF, or equivalent. - Digital, depth-indexed data for all measured parameters: ASCII, CSV, LAS, or WITSML. Note: Surface drilling parameters are recorded at rig sensors and reflect conditions at surface. Equivalent parameters at bit are measured downhole by MWD tools and provided separately under category 05. | .las .ascii .pdf | Data | yes
06.02 | Mud log report | Final mud logging report covering the entire well, issued at the end of drilling. | .pdf | Report | yes
07 | Well path | This dataset is the authoritative reference for all positional information, including True Vertical Depth (TVD), and shall be used for any subsequent interpretation or service. Each wellbore path must be delivered as a continuous set of final, quality-controlled positional data points from surface to TD. All calculations shall include the applied methods (e.g. minimum curvature) and reference/projection information.
07.01 | Original Survey data | Raw survey station measurements (measured depth, inclination, azimuth). Additional fields (e.g. survey tool type, QC indicators) may be provided if available. | .asc, .csv.,.xlsx | Data | yes
07.02 | Final computed wellpath data | Definitive interpolated wellbore trajectory, including TVD, northing, easting, dogleg severity, and closure (or horizontal displacement). | .asc, .las, .csv.,.xlsx | Data | yes
07.03 | Final wellpath report | Summary document covering survey acquisition, QC, corrections applied, methods used, and presentation of the definitive wellpath. | .pdf | Report | yes
08 | Cores | Swisstopo maintains a national drill core storage facility at Mont Terri in St-Ursanne. Depending on existing agreements, cores may also be stored in cantonal facilities. Coring intervals are defined by the operator according to project needs. The selection of cores to be archived will be determined jointly by Swisstopo and/or the cantonal authority, in consultation with the applicant and based on the analyses performed and results obtained. The applicant is responsible for organising the delivery of selected cores to the designated storage facility. Remaining cores are to be retained or disposed of by the applicant at their own expense.
08.01 | Cores | Physical core samples. Maximum core length to be stored: 1 m. | - | Samples | yes
08.02 | Coring operations report | The report describing the coring operations. | .pdf | Report | yes
08.03 | Cores inventory | List including drilling depth, core depth, recovered length, core loss, core quality, and physical storage location (if stored in a cantonal facility). Use the template in Annex C. | .xlsx | Data | yes
08.04 | Core analysis programme & progress | Document(s) outlining the planned RCA/SCAL analyses for both conventional cores and sidewall cores, laboratories involved, expected schedule, and progress updates until final reporting is complete. | .xlsx .pdf | Report | yes
08.05 | Core and Sidewall core custody & status | Updated inventory of all core-derived samples (whole cores, plugs, sidewall cores, thin sections, powders, resin mounts, etc.) showing current physical location, transfers between labs, and final repository status. | .xlsx .pdf | Report | yes
08.06 | Core analysis data | Raw and processed data for all conventional and sidewall-core analyses. The following are considered relevant to geothermal applications: - Routine Core Analysis (RCA): Porosity, Permeability (gas and/or water), Grain density, Core gamma ray and spectral gamma ray - Advanced analyses (Geothermal-focused “SCAL”); - Mechanical properties: uniaxial compressive strength (UCS), triaxial tests, elastic moduli, fracture toughness. - Acoustic properties: compressional and shear velocity, dynamic vs static moduli. - Thermal properties: thermal conductivity, thermal diffusivity, heat capacity. - Mineralogy & petrography: thin sections, XRD, XRF, SEM, automated mineralogy, hyperspectral imaging, clay analyses - Imaging: CT (tomography) and Micro-CT scans (porosity distribution, fractures, heterogeneity). - Magnetic susceptibility | .xlsx .pdf | Data | yes
08.07 | Core and Sidewall analysis lab reports | Laboratory reports documenting analyses performed on conventional cores and sidewall cores. | .pdf | Report | yes
08.08 | Core description reports | Geological, lithological, and petrophysical descriptions of the cores. | .pdf | Report | yes
08.09 | Core connection line | Orientation/connection of cores, shown by core-run connection lines. | .xlsx | Data | yes
08.10 | Cores planar photographs | Digital images of core slabs under white light; ≥ 9000 px/m (≈230 dpi). Filenames must include core number and depth. | .jpg | Images | yes
08.11 | Cores 360 photographs | Digital 360° images of core slabs under white light; ≥ 9000 px/m (≈230 dpi). Filenames must include core number and depth. | .jpg | Images | yes
08.12 | Core plugs photographs | Digital images of core plugs under white light; ≥ 9000 px/m (≈230 dpi). Filenames must include core number and depth. | .jpg | Images | yes
08.13 | Final core report | An integrated report compiling coring operations, core inventory, analyses, laboratory results. | .pdf | Report | yes
09 | Sidewall Cores (SWC) | Sidewall cores (SWC) are small-diameter samples taken at discrete depths from the borehole wall, either by percussion or rotary coring tools. Unlike conventional cores, they are not continuous, but provide point measurements for petrophysical, mineralogical, or geomechanical analyses.
09.01 | SWC operations report | Documentation of sidewall coring operations (tool type, depths attempted, success/failure, recovery). | .pdf | Report | yes
09.02 | SWC inventory | List of all SWC samples, including drilling depth and/or logger's depth, recovered length/volume, recovery success, and current storage location. | .xlsx | Data | yes
09.03 | SWC photographs | Digital photographs of individual sidewall cores under white light, minimum resolution ≥ 9000 px/m (≈230 dpi). Filenames must include well, sidewall core number, and depth. | .jpg | Images | yes
09.04 | Final SWC report | Integrated report summarising sidewall coring operations, inventory, analyses, and laboratory results. | .pdf | Report | yes
10 | Cuttings | Swisstopo maintains a national drill cuttings storage facility at Mont Terri (St-Ursanne). Depending on existing agreements, cuttings may also be stored in cantonal facilities.
10.01 | Cuttings samples | Operators must deliver a washed and dried (<40 °C) representative sample of each original sampling interval. - Each sample must contain 200–250 g of material, packed in transparent plastic boxes. - Labelling: well name, operator, sample ID/number, and depth interval, using a dark waterproof marker. - Delivery: in Rako boxes on pallets to Swisstopo and/or cantonal facility (depending on agreement). - Remaining material is the responsibility of the applicant (to retain or dispose of at own expense). | - | Samples | yes
10.02 | Cuttings inventory | Tabulated list of all cuttings samples, including: - Sample ID/number, depth interval, petrographical/lithological description. - Physical storage location (if in cantonal facility). - Use the spreadsheet template provided in Annex C. | .xlsx | Data | yes
10.03 | Cuttings analysis data | Raw and processed results of laboratory analyses performed on cuttings, e.g.: XRF, XRD, QEMSCAN, SPECCAM, calcimetry, mineralogy, geochemistry. | .xlsx .csv .pdf | Data | yes
10.04 | Cuttings analysis reports | Laboratory reports documenting methods and results, including procedures for drying, cleaning, description, and photography. | .pdf | Report | yes
10.05 | Cuttings photographs | Digital images of cuttings taken under white light. Minimum resolution: ≥ 9000 px/m (≈230 dpi). Filenames must include sample number and depth. | .jpg | Images | yes
11 | Logging While Drilling (LWD) | Logging While Drilling (LWD) data are continuous, downhole, depth-indexed measurements acquired using sensors integrated into the BHA and recorded either in memory and/or transmitted to surface in real time. While LWD enables data acquisition in adverse hole conditions and highly deviated wells where wireline may not be feasible, the range of available tools is nevertheless more limited than with wireline. The master document “Technical Specifications for Data Delivery.docx” contains the full detailed requirements for file naming conventions, content, formats, and data categories applicable to LWD data. The present .xlsx document provides only a summary. Readers should refer to the master document for complete specifications.
11.01 | LWD programme | The logging program is a document jointly prepared by the project owner and the logging service provider for each logging campaign (i.e., a series of logging runs conducted under a single wireline crew mobilization). ). It defines the objectives of the LWD operation, the data to be acquired and de-livered, and the tool configurations and operational procedures. | .pdf | Report | yes
11.02 | Real-Time (RT LWD) data | Limited-resolution datasets transmitted to surface during drilling. | .las .dlis .pdf | Data | yes
08.03 | Memory (RM LWD) data | Full-resolution datasets downloaded from downhole tools after retrieval; LAS, DLIS, PDF. Fully quality-controlled logs, revised by the service provider where necessary and validated by the project owner. Serves as the official reference for interpretation and archiving. | .las .dlis .pdf | Data | yes
08.04 | Processed LWD data (if produced) | Advanced vendor/operator/third party processing (e.g. azimuthal images, NMR T2 distributions, spectroscopy); LAS, DLIS, PDF logplots, processing reports. | .las .dlis .pdf | Data | yes
08.05 | Interpreted LWD data (if produced) | Advanced vendor/operator/third party interpreted (e.g. borehole image interpretation); DLIS, LAS, PDF logplots, interpretation reports. | .las .dlis .pdf | Data | no
08.06 | LWD contractor field reports (if produced) | Operational reports provided by the logging contractor at the end of the campaign, including runs performed, chronology, incidents, QA/QC notes, and calibration certificates. | .pdf | Report | no
08.07 | LWD QC and supervision reports (if produced) | Reports prepared by the project owner or representative, covering run summaries, data quality observations, QC checklists, and non-conformance notes. | .pdf | Report | yes
12 | Wireline Logging (WL) | Wireline logging data are downhole, depth-indexed formation evaluation measurements acquired after drilling, using tools lowered on an electric line. Wireline provides the most complete range of measurements and highest data quality, but is subject to hole conditions and operational constraints. The master document “Technical Specifications for Data Delivery.docx” contains the full detailed requirements for file naming conventions, content, formats, and data categories applicable to wireline logging data. The present .xlsx document provides only a summary. Readers should refer to the master document for complete specifications.
12.01 | WL programme | The logging program is a document jointly prepared by the project owner and the logging service provider for each logging campaign (i.e., a series of logging runs conducted under a single wireline crew mobilization). ). It defines the objectives of the WL operation, the data to be acquired and de-livered, and the tool configurations and operational procedures. | .pdf | Report | yes
12.02 | Rush data (if produced) | Selected logs, typically uncorrected and of limited quality, sometimes over partial intervals, for immediate operational decision support | .las .dlis .pdf | Data | yes
12.03 | Field data | Uncorrected or preliminary-quality data, including all purchased logs, for preliminary evaluation. Usually delivered by the service provider within 24–48 hours post-acquisition. | .las .dlis .pdf | Data | yes
12.04 | Final data | Fully quality-controlled logs, revised by the service provider where necessary and validated by the project owner. Serves as the official reference for interpretation and archiving. Usually delivered within days to weeks after logging. | .las .dlis .pdf | Data | yes
12.05 | Processed WL data (if produced) | Advanced vendor/operator/third party processing (e.g. borehole images, NMR T2, acoustic waveforms); DLIS, LAS, PDF logplots, processing reports. | .las .dlis .pdf | Data | yes
12.06 | Interpreted WL data (if produced) | Advanced vendor/operator/third party interpreted (e.g. NMR interpretation, acoustic anisotropy, cement evaluation); DLIS, LAS, PDF logplots, interpretation reports. | .las .dlis .pdf | Data | no
12.07 | WL contractor field reports (if produced) | Operational reports provided by the logging contractor at the end of the campaign, including runs performed, chronology, incidents, QA/QC notes, and calibration certificates. | .pdf | Report | no
12.08 | WL QC and supervision reports (if produced) | Reports prepared by the project owner or representative, covering run summaries, data quality observations, QC checklists, and non-conformance notes. | .pdf | Report | yes
13 | Vertical seismic profile (VSP) | Vertical Seismic Profiling (VSP) consists of seismic recordings with downhole geophones or accelerometers and a controlled source at surface near the borehole. VSP provides high-resolution time-depth calibration, velocity models, and, in some survey types, seismic imaging around the wellbore.
13.01 | Raw VSP data | All unprocessed downhole seismic recordings, including observer’s logs and geometry files (SEG-D, SEG-2, or equivalent). | .segy | Data | yes
13.02 | Processed VSP data | Fully processed datasets, including: - Check-shot surveys: time–depth tables and velocity profiles (ASCII, CSV, PDF plots). - Zero-/offset/walkaway VSP (if acquired): corridor stacks, gathers, migrated images (SEG-Y, PDF). - Headers must clearly describe polarity, processing steps, and domain (TWT or depth). | .segy | Data | yes
13.03 | VSP reports | Documentation of acquisition parameters, tool configuration, survey geometry, processing workflow, QC, and results (PDF). | .pdf | Report | yes
13.04 | VSP interpretation report (if produced) | Higher-level interpretation of VSP results (e.g., structural tie to surface seismic, anisotropy studies). | .pdf | Report | no
14 | DST-Hydro-Prod tests | This category covers well-scale tests of hydraulic behaviour and productivity, including drill stem tests (DSTs), injection/fall-off tests, pumping/recovery tests, air-lift tests, and production logging. Fluid samples collected during such tests shall be reported under Chapter 14 (Fluids).
14.01 | Hydrogeological well tests | Hydrogeological well tests (including DSTs, injection, fall-off, pumping/recovery, and air-lift tests): raw and processed pressure–time and flow-rate data, with interpreted transmissivity/permeability values. | .xlsx .csv .las .pdf | Data | yes
14.02 | Production logging tests (PLT) | Downhole production logging of flow profiles (e.g. spinner, pressure, temperature). Deliver raw depth-indexed logs, processed curves, and logplots. | .xlsx .csv .las .pdf | Data | yes
14.03 | Well test plots | Appropriately scaled graphical plots of raw and processed measurements (pressure, rate, temperature) as a function of time at each test depth. | .pdf | Graphical plot | yes
14.04 | Well tests programme and execution reports | Documentation of test objectives, programme, execution conditions, tool configurations, and parameters applied. | .pdf | Report | yes
14.05 | Well tests interpretation reports | Interpretation of test results, including derived reservoir/hydrogeological parameters. | .pdf | Report | no
15 | Fluids | This category covers sampling of formation fluids during drilling, testing, or production, and the results of laboratory analyses performed on these fluids.
15.01 | Fluid sampling report | Documentation of sampling operations (date, depth, method, conditions, preservation). | .pdf | Report | yes
15.02 | Fluid inventory | List of samples collected, with identifiers, depth, date, and current storage location. | .xlsx .csv | Data | yes
15.03 | Laboratory analyses | Raw and processed results of fluid analyses, including as relevant: - Physical properties: density, viscosity, compressibility, phase behaviour. - Chemical composition: major ions, trace elements, gases (CO₂, H₂S, CH₄, N₂), isotopes (δ¹⁸O, δD, δ¹³C, etc.). - Scaling and corrosion potential: silica saturation, calcite/aragonite saturation, corrosion indices. - Environmental parameters: salinity, pH, alkalinity, redox potential. | .xlsx .csv .pdf | Data | yes | [6 empty] | Follow Hydrochemical characterisation of geothermal fluids – Guideline for sampling and analyses
15.04 | Laboratory reports | Contractor laboratory reports with methods, QA/QC, and certified results. | .pdf | Report | yes
16 | Pressure tests | This category covers in-situ pressure measurements and hydraulic testing of formations. Mechanical rock strength tests (UCS, triaxial, etc.) are covered under Section 09 (Cores) and Section 21 (Geomechanics). Wellbore-related integrity tests are covered in Section 17.
16.01 | Formation pressure measurements | Pressure surveys (e.g. RFT/MDT or equivalent), build-up/gradient tests. Results shall include pressure vs. depth profiles and interpreted hydrostatic gradients. | .xlsx .pdf | Data | yes
16.02 | Hydraulic injection and stimulation tests | Mini-frac, micro-frac, diagnostic fracture injection tests (DFITs), and injection/fall-off tests. Data shall include pressure–time records, flow rates, and interpreted transmissivity/permeability values. | .xlsx .pdf | Data | yes
16.03 | Pressure test reports | Documentation of acquisition conditions, tool configuration, intervals tested, QC, and results. | .xlsx .pdf | Report | yes
17 | Pressure Integrity Tests | This category covers tests performed to determine the strength of the open formation and establish the safe mud weight window. Typical tests include Formation Integrity Tests (FIT), Leak-Off Tests (LOT), and Extended Leak-Off Tests (XLOT). Notes: - All test results must be explicitly tied to measured depth, true vertical depth, casing shoe depth, and mud weight at the time of the test, so they can be directly used for geomechanical modelling (Section 21). - If no FIT/LOT/XLOT was performed at a casing shoe, the operator must explicitly state this in the final drilling report.
17.01 | Raw test data | Unprocessed pressure vs. time (and if available, volume/flow rate) records acquired during each test. | .xlsx .csv .pdf | Data | yes
17.02 | Processed data | Results of each test, including: - Leak-off pressure, fracture initiation pressure, fracture propagation/closure pressures (as applicable). - Equivalent mud weight / fracture gradient at test depth. | .xlsx .csv .pdf | Data | yes
17.03 | Test reports | Documentation of test objectives, methods, depth, mud weight, execution conditions, and results. The report should also identify anomalies (e.g. premature breakdown, poor test quality). | .pdf | Report | yes
18 | Cement | This category covers cementing operations and the evaluation of cement and casing integrity. Note: For cement evaluation logs and contractor interpretation reports, see Section 12 Wireline Logging
18.01 | Cementing program | Planned cementing operations, including slurry design, additives, volumes, densities, rheology, placement techniques, and operational parameters. | .pdf | Report | yes
18.02 | Cementing job reports | Actual cement placement reports, including pump charts, volumes, densities, returns, job execution chronology, deviations from the program, and QA/QC observations. | .pdf | Report | yes
18.03 | Casing Integrity Tests (CIT) | Pressure tests of casing and cemented annuli to verify well barrier integrity. Data must include raw pressure–time records, test parameters, and interpreted maximum allowable casing pressure. | .pdf | Report & Graphical Plot | yes
19 | Geology | All integrated geological interpretations, syntheses, and models derived from drilling and post-drilling analyses.
19.01 | End of Well Geological Report (EOWGR) | Final geological synthesis report describing lithology, stratigraphy, facies, structural observations, and geological conclusions from the well. - Includes final lithostratigraphic tops (MD and TVD). - Delivered as a single compiled PDF with appendices. | .pdf | Report | no
19.02 | Stratigraphic data | Final table of the tops (MD) for: - Detailed lithology (standardized lithology used for the symbology in the logs + lithological descriptions) - Chronostratigraphy (period, epoch, stage) - Lithostratigraphy (formation, member, bed) | .xlsx | Data | yes
19.03 | Geological cross-sections and correlation panels (if produced) | 2D cross-sections and correlation panels not embedded in the main report. | .pdf | Graphical plot | no
19.04 | Biostratigraphy / micropaleontology reports (if acquired) | Reports and tabulated data from biostratigraphic or micropaleontological analyses. | .pdf .xlsx | Report | no
19.05 | Geological / hydrogeological / geomechanical models (if produced) | 2D/3D models of lithology, facies, and structures, as well as static property models relevant to hydrogeology or geomechanics. PDF (maps, figures); digital model files in standard formats (e.g. Petrel, shapefiles). | .pdf Original software format | Model | no | [6 empty] | Export format to be discussed case by case.
20 | Petrophysics | All petrophysical interpretations, formation evaluations, and advanced workflows derived from wireline, LWD, mud logging, and core data.
20.01 | Composite well logs (if produced) | Final composite log integrating the main curves, fully quality-controlled, depth matched, environmentally corrected, conditioned, and merged. A report explaining the processing and merging workflow must be included. Deliverables: Report (PDF or Excel), LAS file (digital curves), logplots in PDF at scales 1:200 and 1:1000 | .pdf .xlsx .las | Data Graphical Plot Report | no
20.02 | Formation evaluation datasets (if produced) | Results of formation evaluation using deterministic and/or stochastic approaches, including: - Mineral models - Porosity (clay-bound, effective, and total) - Fluid properties (e.g. salinity, fluid volumes) Deliverables: - LAS file including: - Input curves (from the composite log, see 20.01) - Output curves (flags, mineral volumes, porosity types, fluid volumes, permeability, etc.) - Processing parameters - Logplots in PDF at scales 1:200 mMD and 1:1000 mMD - Methodology report documenting workflow, assumptions (e.g. clay bound porosity), parameters used (e.g. log end-members, and any core-calibrated parameters (e.g. porosity-permeability transforms, mineral density values) | .las .pdf | Data Graphical Plot Report | no
20.03 | Borehole image analysis (if produced) | Interpretation of borehole image logs (see Sections 8 and 11 for raw log data). Results shall include: - Fracture identification and classification (natural, induced, drilling-related) - Structural dips, bedding, faults, and sedimentary features - Image log plots with interpretation overlays at 1:20, 1:40, and 1:200 scales - Images oriented to north, unless in deviated sections where they shall be oriented to top of hole - A dynamic image track without dip picks displayed alongside the same image track with dip overlays - Derivation of in-situ stress orientations and stress regime classification (from breakouts, drilling-induced fractures, and borehole deformation) - Report including methodology, fracture population analysis, regional structural context (stress regime, etc.), and comparison with seismic observations | .pdf .xlsx .las | Data Graphical Plot Report | no
20.04 | Cement evaluations | Interpretation of cement evaluation logs (see Section 11 for raw log data). Results shall include: - Cement bond quality and zonal isolation assessment zone by zone, summarized in a table - Quantitative indices (CBI, VDL interpretation, USIT/CAST outputs) - Processed / Interpreted log plots and summary report Deliverables: LAS/DLIS (derived curves), PDF (plots, report). | .las .pdf | Data Graphical Plot Report | no
20.05 | Other advanced workflows | Additional petrophysical analyses beyond standard formation evaluation, which may include: - Permeability modelling - Formation temperature modelling (e.g. Horner plot) - Electrofacies classification - NMR interpretations (e.g. T₂ distribution, bound/free fluid volumes, permeability estimation) - Advanced formation evaluation techniques, e.g. Monte Carlo simulations, probabilistic/uncertainty analysis | .las .dlis .pdf | Data Graphical Plot Report | no
21 | Geomechanics | All geomechanical models, interpretations, and synthesis reports derived from well data and laboratory analyses.
21.01 | Elastic properties from logs | Elastic parameters derived from sonic and density logs: Young’s modulus, Poisson’s ratio, shear modulus, bulk modulus. Input logs should be from the composite log, see 20.01. | .las | Data | no
21.02 | Sonic- and image-based advanced analyses | Specialized interpretations from sonic / borehole image logs, e.g.: - Anisotropy analysis (cross-dipole) - Radial damage / breakout analysis Format: LAS/DLIS (derived curves), PDF (plots, report). | ,las .dlis .pdf | Data Graphical Plot Report | no
21.03 | Pore pressure prediction models | Pre-drill and/or post-drill models, calibrated to well measurements. | .xlsx .pdf | Data Graphical Plot | no
21.04 | Fracture gradient and mud weight window models | Derived fracture gradient curves and safe drilling windows, integrating results from pressure integrity tests (see Chapter 17). | .xlsx .pdf | Data Graphical Plot | no
21.05 | Mechanical Earth Model (MEM) | Integrated 1D or 3D MEM including elastic and strength properties, stresses, pore pressure, and fracture gradient. Format: LAS (curves), specialized software files (models), PDF (reports). | .las .pdf Original software format | Data Graphical Plot Report | no
21.06 | Geomechanical synthesis report | Final integrated report documenting input data (logs, lab tests, cores, pressure tests), methodology, calibration, and results. Includes implications for drilling, reservoir stability, and long-term storage integrity. Note: Raw laboratory test results (UCS, triaxial, creep, etc.) are delivered under 08 Cores. Only derived properties and their integration into geomechanical models are included in this chapter. | .pdf | Report | no
22 | Post-well documentation | All final well-level reports and documentation produced after drilling, excluding advanced interpretation reports (covered in Chapters 19–21).
22.01 | End of Well Report (EOWR) | Operator’s final report summarizing the well, typically including: - Drilling operations (daily summary, chronology, NPT, key events) - Mud systems and performance - Casing and cementing operations - Logging and testing operations - HSE performance and incidents - Lessons learned and recommendations | .pdf | Report | yes
22.04 | Completion / Workover / Plug and Abandonment Report (if applicable) | Reports documenting well completion operations, later workovers, or final plug and abandonment. Content may include: - Completion design and execution (tubing, packers, perforations, stimulation, wellhead equipment) - Workover objectives, execution, and results - P&A procedures, plugs set, barriers verified, regulatory compliance Note: These reports may be delivered at a later stage in the well lifecycle, separate from the drilling EOWR/EOWGR. | .pdf | Report | yes
22.05 | Supplementary reports (if not included in the EOWR) | In cases where the operator or service providers issue separate final reports (e.g. mud, cementing, directional drilling, HSE), these shall also be provided. | .pdf | Report | yes
23 | Miscellaneous documentation | Documents and datasets related to drilling operations that do not fit into the preceding categories but provide useful supporting information.
23.01 | Data inventory (Annex C) | Annex C template must be filled with: - Overview of the well sections - Summary of all well-logging operations completed in the well - List of all files provided to swisstopo - List of cuttings and cores delivered - Metadata | .xlsx | Information file | yes
23.02 | Seismic monitoring report | Report(s) on seismic monitoring during the drilling operations. Raw data is not requested, as it is usually already stored by the Swiss Seismological Service (SED) | .pdf | Report | yes
23.03 | Springs and ground water monitoring data | Raw data of springs and ground water monitoring before, during and after the drilling operations | .xlsx or GIS file | Data | yes
23.04 | Springs and ground water monitoring report | Report(s) on springs and ground water monitoring before, during and after the drilling operations | .pdf | Report | yes
23.05 | Environmental monitoring report | General environmental monitoring report | .pdf | Report | yes